Support for Coherent Implementation of the Environmental Dimension of the Sustainable Development Goals

Statistical training and roadmap development for Guyana

Prepared for:						Submitted by:

Mr. Peter Morrison					Robert Smith			
EcoEcoAnalysis					Principal
 							Midsummer Analytics

Date: November 13, 2019

# Introduction

As a component of the study Support for Coherent Implementation of the Environmental Dimension of the Sustainable Development Goals, Midsummer Analytics provided training on environmental statistics to experts in Guyana and assisted the Department of Environment with initial steps toward development of a roadmap for environmental statistics.

This report provides:

- a summary of the statistical training undertaken (Section 2 and annexes 1 and 2)

- a summary of the status of development of Guyana’s National Strategy for the Development of Statistics and the opportunity this presents for the development of a roadmap for environmental statistics (Section 3)

- our views on the elements required in a roadmap for environmental statistics and the considerations for the Department of Environment in working toward its creation (Section 4)

- our specific recommendations to the Department of Environment to begin the process of establishing Guyana’s roadmap for environmental statistics (Section 5).

# Summary of statistical training

Midsummer Analytics undertook two missions to Guyana in support of our statistical training. The first was a two-day mission to Georgetown (February 7-8, 2019) to participate in the project inception meetings hosted by the Guyanese Department of Environment (DoE) and the United Nations Environment Programme. The mission consisted of a one-day inception workshop with a range of governmental and non-governmental experts (February 7) followed by a day of bilateral meetings with representatives of key government departments (see Annex 1 for the mission agenda and a copy of the presentation we gave during the inception workshop).

The overall objectives of the inception mission were to introduce the project to representatives of the Guyanese government and to seek their engagement in it. The mission provided us with an opportunity to meet the main Guyanese experts, to explain Midsummer Analytics’ role in the project to them and to seek their input on how we could best meet their needs. Based on discussions during the workshop, we were able to:

- establish contact with key environmental statistics experts, and

- propose an initial set of topics to be covered during the subsequent training workshop, which was then further refined through e-mail discussion with the DoE point of contact and the UNEP Project Manager.

The second mission (Georgetown, August 6-8, 2019) was devoted to delivery of the statistical training itself. The workshop agenda and training materials are included here in Annex 2. Robert Smith of Midsummer Analytics delivered the majority of the training over the three days of the workshop. The training approach was a combination of formal presentations, practical examples to reinforce learning in small and large groups and question and answer sessions. Some thirty Guyanese experts actively participated in the workshop, demonstrating a good level of prior knowledge and an appetite for deepening and broadening their understanding of environmental statistics. The topics covered during the workshop included:

- the UN Fundamental Principles of Official National Statistics

- the UN Framework for the Development of Environment Statistics (FDES)

- the UN Environment Statistics Self-Assessment Tool (ESSAT), and

- the principles of statistical roadmaps, and

- identifying the needs, gaps and priorities for Guyana’s environmental statistics, particularly in the areas of energy and land-use statistics.

Ample time for questions and answers was provided at all points during the training to allow participants to probe more deeply where they wished. The active discussions during the sessions showed that participants were happy to take advantage of this opportunity. Participants expressed satisfaction with the training.

# Developing a roadmap for environmental statistics in Guyana

The focus of the statistical training provided by Midsummer Analytics during the training workshop and the advice offered to the DoE following the workshop was – at the request of the UNEP project manager – focused on assisting DoE with the development of a roadmap to improve Guyana’s environmental statistics. In this section, we outline the practical steps DoE is encouraged to take toward the development of this roadmap, taking particular note of the fact that the country is currently preparing an overall national strategy for the development of statistics. In the following section, we provide our opinions on how DoE should approach development of each element of the environmental statistics roadmap.

## Guyana’s National Strategy for the Development of Statistics

In May 2017, the Government of Guyana launched a process to develop – for the first time – a National Strategy for the Development of Statistics 2019-2025 (NSDS). The process is being led by the Guyana Bureau of Statistics (BoS) with the assistance of PARIS21 and the Inter-American Development Bank (IDB). The NSDS will be the master plan for the short-, medium- and long-term development of Guyana’s national statistical system (NSS) and its official statistics. As such, it will provide the country with a strategy for building capacity across the NSS and a vision for where the NSS should be by 2025, with milestones for getting there. The NSDS will provide a framework for assessing user needs, for setting priorities and for building capacity to meet needs in a coordinated and efficient manner. It will help Guyana mobilise, harness and leverage resources (both national and international) and provide a basis for results-oriented management of the NSS.

### The vision for Guyana’s NSDS

By the end of the implementation of Guyana’s first NSDS in 2025, the NSS will have been transformed into a well-coordinated, well-resourced, modern, innovative, technology-driven system trusted to produce and disseminate comprehensive, reliable, accessible, high-quality statistics that meet users’ needs for information on the social, economic and environmental conditions of the people of Guyana in a coordinated, timely and efficient manner and according to international standards and codes of practice. The NSS will be effectively managed by the Guyana Bureau of Statistics (BoS) and will operate in a culture that emphasizes use of statistics for evidence-based decision-making, monitoring and evaluation. Official social, economic and environmental statistics will be integrated into national development priorities and objectives, will promote regional integration and will support Guyana’s commitments to sustainable development and the reduction of poverty. The NSS will commit to:

- adhere to professional principles and ethical standards and practices

- collaborate and coordinate among its members

- meeting user needs

- facilitating data access

- statistical quality

- efficient use of financial and human resources

- minimizing burden on respondents

- transparency and accountability, and

- continuous learning.

### Developing and implementing the NSDS

To date, three reports have been produced in support of development and implementation of the NSDS:

- an assessment of Guyana’s statistical capacity (May 2017)

- an analysis of the NSS’s strengths, weaknesses, opportunities, threats (January 2018), and

- a roadmap toward the creation of the NSDS prepared by PARIS21 (second half of 2018).

Based on these reports and on more recent discussions we understand to have occurred during the validation workshop referred to in Footnote 6, the main decision-making and coordinating mechanism for NSDS development and implementation is proposed to be a NSDS Steering Committee (SC-NSDS). In addition, a multi-sector Technical Working Group (TWG-NSDS) is proposed as a second tier of governance. The SC-NSDS is proposed to comprise the following individuals representing a cross-section of the NSS:

- the Chief Statistician of the BoS (chairperson)

- the Chairperson of the TWG-NSDS (deputy chairperson)

- the NSDS coordinator, as a non-voting ex officio member (secretary)

- a representative of the Bank of Guyana

- a representative of the Ministry of Finance

- a representative of the Department of Energy

- a representative of the Special Committee on Statistics Legislation

- a representative of the Special Committee on Information and Communication Technology

- a representative of the University of Guyana

- a representative of the Inter-American Development Bank

- a representative of the UN System in Guyana, and

- two representatives of civil society organizations

The TWG-NSDS, for its part, is proposed to comprise individuals representing the interests and views of the economic, demographic, social, energy, natural resource and environmental sectors. The specific institutions to be invited to nominate representatives for the TWG-NSDS have not yet been identified.

Special committees are proposed to expedite activities in two areas critical to the transformation and coordination of the NSS:

- drafting of new statistical legislation for Guyana consistent with CARICOM best practice, and

- coordination of information and communication technology for the NSS to ensure system interoperability; data sharing, storage, security; and open data for official statistics as a public good.

## The Department of Environment’s role in the NSDS

The DoE was not engaged in the NSDS process during its first two years, only having become involved in October 2019 when it took part in the validation workshop noted in Footnote 6 and subsequently held a bilateral meeting with Mr. David Clement, the consultant guiding the NSDS process.

In spite of the DoE’s absence from the process during its first two years, the 2018 PARIS21 NSDS roadmap indicated that improvement of Guyana’s environmental and climate change-related statistics was a strategic objective for the NSDS. Given this – and the fact that development of the NSDS has not proceeded as quickly as planned since 2017 – the DoE now has a significant opportunity to engage as a full partner in the development of the NSDS. In particular, assuming that no other department/agency has already been assigned the role,

the DoE has an opportunity to lead the development of the environmental sub-component of the NSDS, which we call the roadmap for Guyana’s environmental statistics.

Given the strategic importance of environmental statistics to Guyana, the DoE is urged to seize the opportunity to lead the development of the environmental statistics sub-component of the NSDS - the roadmap for environmental statistics – and to ensure its full integration into the NSDS and its plans for the improvement of Guyana’s overall national statistics.

To this end, the DoE is encouraged to propose:

- that it be invited to name a representative to join the proposed SC-NSDS, on the grounds that environmental statistics are of strategic importance to the country given the prominence accorded environmental conservation in the national development programme laid out in the Green State Development Strategy – Vision 2040 (GSDS), and

- that it offer to have the representative it names to the proposed TWG-NSDS serve as the group’s chairperson.

Assuming that no department is already leading the development of the environmental component of the NSDS and that BoS would welcome DoE’s leadership in this regard, DoE should immediately assign a small team to establish the mechanisms by which it will lead the development of the roadmap and ensure its integration into the NSDS. In doing so, DoE should recognize that playing this role will require investing a meaningful amount of time and effort on behalf of DoE staff but that this investment is justified by the need to ensure full consideration of environmental statistics in Guyana’s NSDS.

The DoE is encouraged to create and manage two inter-departmental groups (parallel to those proposed for the overall NSDS) to develop the roadmap:

- a Steering Committee for Environmental Statistics Roadmap (SC-ESR) comprising senior managers from each relevant department/agency and charged with overseeing the development of the high-level aspects of the roadmap, and

- a Technical Working Group on Environmental Statistics Roadmap (TWG-ESR) comprising technical experts from each relevant department/agency and charged with addressing the technical aspects of the roadmap (methods, definitions, etc.).

Each group should have a clear terms of reference and workplan outlining its objectives and the activities it will undertake (see Section 4 for further details of the activities related to development of the roadmap).

Once the necessary inter-department mechanisms have been established, DoE should manage these groups to successfully develop the roadmap and ensure its integration into the final NSDS. Careful attention will be required to the development of the other elements of the NSDS to ensure the roadmap’s full coherence with the overall strategy for the improvement of Guyana’s national statistics. For example, consideration will have to be given to ensuring interoperability of any information systems proposed for environmental statistics (such as the Environmental Information Monitoring and Management System already under development at DoE) with those that might be developed as part of the NSDS.

The activities related to defining the elements of the roadmap are outlined in Section 4 (and covered in much of the material presented during the training workshop). These activities provide a framework for the work of the SC-ESR and TWG-ESR and DoE is encouraged to use them (and the material from the training workshop) to design the groups’ formal terms of reference and workplans. It should do so in a flexible manner that recognizes 1) there is more than one way to approach development of a roadmap and the approach laid out in Section 4 and in our training material is just one option among many; and 2) the workplans of the groups developing the environmental statistics roadmap must be coherent and consistent with those of the SC-NSDS and TWG-NSDS.

# Creating Guyana’s roadmap for environmental statistics

During the August 2019 training workshop, we devoted considerable time to discussing the elements of statistical roadmaps, which were defined in broad terms as:

- the “starting point” and “end points” for the roadmap

- the context for the roadmap

- the constraints on the roadmap

- the steps in the roadmap, and

- the contingencies needed for the roadmap.

Each of these elements is discussed in turn below. For each, we provide advice to the DoE in terms of developing the element.

## Defining the starting and end points

As noted during the training workshop, a roadmap is simply a plan to get an organization from where it is to where it wants to be. Roadmaps are unnecessary for some journeys and essential for others. Most people do not need a roadmap to get to work every day, as they know the route well. But when embarking on long, complex journeys, sensible people will not leave without a roadmap in hand. In other words, when there is a lot at stake, having a roadmap as a guide is a good idea.

Roadmaps are generally high-level and brief. They map out journeys in broad terms, not every detail. They don’t say much about the specific tools needed along the way, but they provide a framework for thinking about and choosing those tools. Action plans are usually put in place to execute roadmaps once they have been developed and that is where the tools needed to implement the roadmap would be defined. This report is about defining the roadmap for Guyana’s environmental statistics only; definition of any action plan for its implementation would be a separate activity undertaken only once the roadmap was defined and agreed upon.

It is important to recognise that creating a roadmap when an organization does not know where it is in the first place will not prevent it from wandering. Likewise, creating a roadmap without a destination in mind will not make one suddenly appear. This is why the first element in creating any roadmap is an articulation of the starting point (where the organization finds itself today) and the destination (where it wants to be at some specified point in the future). A roadmap’s destination is often referred to as its vision. In the case of the NSDS, for example, the proposed vision is outlined in Section 3.1.1 as we understand it. We offer our proposal for the vision for Guyana’s environmental statistics next.

### Defining the vision for environmental statistics in Guyana

The starting point for environmental statistics in Guyana could be stated as follows:

Environmental statistics in Guyana today do not meet the needs of the Government, business or the public. The statistics suffer from poor quality in terms of relevance, accuracy, timeliness, accessibility, coherence and interpretability. Environmental statistics capacity is spread across many ministries, departments, agencies with little coordination and no obvious leader. As a result, the statistics are not adequate for evidence-based decision-making or for monitoring and evaluating progress against the nation’s domestic and international environmental commitments, such as the GSDS and SDGs. In light of the above and of the planned development of Guyana’s first NSDS, there is an urgent need to improve Guyana’s environmental statistics and to ensure their full inclusion in the NSDS.

Given the above starting point and drawing inspiration from the NSDS vision, the vision for Guyana’s environmental statistics could be stated as follows:

By the end of the implementation of the NSDS in 2025, Guyana’s national environmental statistics system (NESS) will have been transformed into a well-coordinated, well-resourced, modern, innovative, technology-driven system trusted to produce and disseminate comprehensive, reliable, accessible, high-quality environmental statistics that meet users’ needs in a coordinated, timely and efficient manner and according to international standards and codes of practice. The NESS will be effectively managed by the Guyana Bureau of Statistics in partnership with the Department of Environment and will operate in a culture that emphasizes use of environmental statistics for evidence-based decision-making, monitoring and evaluation in relation to Guyana’s domestic and international environmental commitments. Official environmental statistics will be integrated into national development priorities and objectives, will promote regional integration and will support Guyana’s commitments to sustainable development and conservation of the environment. The NESS will commit to:

  - adhere to professional principles and ethical standards and practices

  - collaborate and coordinate among its members

  - meeting user needs

  - facilitate data access

  - ensure statistical quality

  - use financial and human resources efficiently

  - minimize the burden on respondents, and

  - promote transparency, accountability and continuous learning.

The above starting point and vision are offered as proposals only. They must by confirmed by the SC-ESR (or whatever body is ultimately created to lead development of the roadmap). It is strongly advised that the UN Environmental Statistics Self-Assessment Tool (ESSAT) and/or regional assessment tools (such as that developed in St. Lucia) be applied in confirming the starting point. Such tools have been purpose-built to assist countries in assessing the status of their existing environmental statistics.

As for the vision for Guyana’s environmental statistics, it will have to be spelled out both in high-level terms (as we have done above) but also in terms of the specific environmental statistics the country requires. Again, though, given the high-level nature of roadmaps, the statistics should be identified in relatively broad terms; for example, the need for statistics on stocks of forest resources might be identified in the roadmap without going so far as to list the specific variables to be measured. The GSDS, SDGs and other MEAs should be looked to as important policy drivers of statistical needs. We suggest, as well, that non-policy frameworks should also be considered in defining statistical needs. In particular, the so-called “core set” of 100 statistics identified in the UN Framework for the Development of Environment Statistics (FDES) should be considered, as it is an internationally-agreed set every country is encouraged to compile. While not all core FDES statistics will be relevant in Guyana, many of them will be. Between the FDES core set and the set of statistics implied by the needs of the GSDS, SDGs and other MEAs, it should be relatively straightforward to clearly outline a core set of environmental statistics for Guyana in the roadmap.

## The context for the roadmap

Understanding the context in which roadmaps are developed is key to their success. Failing to account for an important element of context – for example, an informal but important institutional relationship – can undermine implementation of a roadmap. Even though context is not determined by roadmaps, it shapes them and therefore cannot be ignored. In the case of Guyana’s roadmap for environmental statistics, context must be understood in terms of:

- the organizations (public and private) relevant to the demand for and production of environmental statistics and their inter-relationships (both formal and informal)

- government environmental and sustainability policies and priorities, both domestic and international (notably the GSDS and the SDGs), and

- national, regional and international economic, environmental and social trends and forces.

Understanding both the context today and how context is likely to evolve during the course of the roadmap’s execution is important. How might government priorities evolve in the next years and how could this impact the demand for environmental statistics? Considering such questions, even if they cannot be fully answered, will result in a roadmap with greater resilience to external shocks (including shifts in policies).

The ESSAT provides an excellent tool for documenting the current context. Institutions, mandates, inter-relationships, policies and priorities are all easily assessed following the framework it lays out. As assessing current context is largely a technical exercise, this could be undertaken by the TWG-ESR, especially if done using the ESSAT.

Understanding the likely evolution of context is more difficult. This requires a careful situational scan from a strategic viewpoint and, therefore, would be best done by the SC-ESR with its more senior representatives. Both users and producers of statistics should be involved in assessing the possible evolution of context.

## Constraints on the roadmap

Every activity faces constraints. It is preferable that these be accounted for explicitly when developing roadmaps, as failure to do so can result in underestimation of the challenges of implementation. Constraints may include:

- who must be brought on the journey (i.e., who are the stakeholders) and who is not coming along but needs to be kept aware of progress?

- the resources (skills, knowledge, tools, money, time) available, and

- how risky the journey is and the risk tolerance of stakeholders.

### Stakeholders

If an important stakeholder is forgotten, the whole roadmap can be undermined. For example, a statistical roadmap that does not include both users and producers will likely fail. Key stakeholders for Guyana’s environmental statistics roadmap may include:

- the BoS

- central government agencies (Presidency, Finance)

- line ministries and departments (Natural Resources, Agriculture, Environment, etc.)

- key domestic agencies (GEA, GLSC, EPA, GGMC, etc.)

- international partners (PARIS21, IDB, UN)

- households

- businesses

- community groups (indigenous and non-indigenous)

- university researchers, and

- media.

An important role for the DoE in establishing the institutional structures to guide development of the roadmap will be to ensure that no important stakeholder is somehow left unrepresented in those structures, or without a mechanism to provide input. The above list can be taken as a starting point for this only.

### Resource needs and availability

A clear and honest assessment of required and available skills, knowledge, tools, money and time is essential when developing roadmaps. It is better to delay a journey than to embark without sufficient resources to reach the destination.

Since objectivity is key in assessment of resources, such assessment may be best done by third parties. Consultants may be hired, for example, to assess the skills, knowledge and tools available within government agencies. Consultants are more like to be objective in their assessments than are the agencies themselves. Assessing available human resources is straightforward and could also be done by third parties or by the TWG-ESR. Assessing available financial resources is less straightforward, as it may require access to confidential budget information. This is likely best done by the TWG-ESR (or a sub-committee of the SC-ESR).

Assessing the need for resources is, obviously, more complex than assessing their availability. It is, moreover, not an exact science. An honest effort at assessing needs will acknowledge the inherent uncertainty in doing so; for example, by putting ranges around resource requirements. Needs assessment is likely best done by SC-ESR (as its more senior representative will have the perspective required to honestly assess needs) with the assistance of the TWG-ESR and/or third parties with direct experience in environmental statistics (e.g., consulting firms with staff experienced in the collection of official statistics).

Once resource availability and needs have been assessed, resource gaps can be identified and prioritized. Prioritization of gaps is the next step, as it is unlikely that all gaps in environmental statistics will be filled in Guyana even if the government commits additional resources through the roadmap.

### Risks

Every journey involves a certain amount of risk. Risk must be honestly assessed and compared against stakeholders’ tolerance for it. The lowest stakeholder risk tolerance might define the risk tolerance for the entire roadmap. For example, in the case of breaches of respondent confidentiality – a perennial concern in the world of official statistics – the BoS may represent the agency with the lowest risk tolerance (since it has, in principle, the most to lose if respondents lose confidence in the ability of the NSS to safeguard their private data). The BoS’ approach to ensuring confidentiality may, therefore, have to be adopted by all producers of environmental statistics in order for the BoS to “buy in” to the roadmap.

Tolerance for respecting data quality standards is another example. Science-based members of the NESS may have a low tolerance for data that fall short of standards, since their reputations may hinge on their ability to produce highly accurate data. Tolerance for change is yet another example. Roadmap implementation will inevitably involve changes in the operations of NESS members, some of which may be painful. The transformation and modernization process will mean that business-as-usual can no longer be the order of the day. Organizational restructuring may lead to loss of positions in some agencies and increases in others, creating employee resistance. Changes in organizational culture and working arrangements may disrupt long-standing processes with which staff are comfortable. All of this needs to be considered during development of the roadmap. The identification of risks to be assessed would be best undertaken by the SC-ESR. As a starting point, the following categories might be considered:

- privacy protection

- data quality (relevance, accuracy, timeliness, accessibility, coherence and interpretability)

- resistance to change

- budget

- human resources

- schedule

- changes in government or public priorities, and

- international support.

Once the risk categories are identified, assessing the risk tolerance of the various stakeholders against each category could be undertaken by the TWG-ESR, as it is a largely technical exercise. Strategies to mitigate risk should be assessed at the same time.

## Identifying and prioritizing steps in the roadmap

Although roadmaps are not meant to be detailed (as noted earlier, action plans are normally put in place to implement roadmaps), they nonetheless must discuss the steps in a journey at least in broad terms. Ideally, they should also sequence the steps in terms of priority and identify those that can be carried out simultaneously and those that must be completed before others can begin. For example, in a statistical roadmap, it may be necessary to finish data collection and reporting for some statistics before beginning methodology development for others if there are wide variations in the relevance of statistics in terms of meeting users’ needs.

There are many ways in which steps in a roadmap might be prioritized. In the case of Guyana’s roadmap for environmental statistics, prioritization should follow the Government’s domestic priorities as identified in the GSDS’ monitoring and evaluating framework. Priorities for international reporting – particularly against the SDGs – should also be considered.

Likely steps in any roadmap for statistics would include (in no particular order):

- staffing and training

- development of cooperation mechanisms among members of the NESS, including legal and policy development

- identification of users’ needs and comparison of those needs with existing statistics (gap analysis)

- methods development

- data collection

- reporting and analysis, and

- review of successes and failures.

Though each of the above would obviously have many sub-steps, the urge to include too much detail in the roadmap must be avoided. It is most important to gain agreement on the high-level steps needed to address the improvement of the NESS. Once this has been achieved, the details needed to implement the roadmap can be laid out in the associated action plan. If too many details are included in the roadmap itself, this may stymie approval of it because of possible disagreements over small, relatively inconsequential, details.

## Identifying contingencies

In spite of the best intentions, roadmaps rarely unfold exactly as envisioned at their creation. As future-oriented documents, they are unavoidably burdened by uncertainty about how the world will actually unfold. For this reason, it is wise to embed contingencies in the form of alternative pathways in any roadmap – if the preferred pathway winds up blocked by some unforeseen (or even foreseen) event, the alternative pathway is ready and waiting to be followed. Delays and losses of key resources are part of any journey and, at a minimum, these must be planned for; contingencies must be in place in the case of loss of key project managers, for example. Likewise, a certain amount of delay (from myriad, predictable causes) should be assumed in any journey and this must be accounted for by establishing realistic timelines. In this way, inevitable delays will not overly disrupt progress. In the case of statistical roadmaps, other likely roadblocks include survey methods that fail, uncooperative respondents, faulty technology, staff turnover, budget cutbacks and interdepartmental disagreements. Contingencies for all of these should be considered when creating the roadmap. It could be agreed, for example, that international datasets will be used as the fallback if methods proposed for compilation of a given statistic turn out to be ineffective.

Keeping track of progress at milestones along the route is important. Again, as high-level documents, roadmaps should not include large numbers of milestones – just enough to provide opportunities to take stock and adjust at key points in the journey. If progress has not been as expected at a given milestone, contingency plans can be put into action. Milestones can be regular or task-specific. An annual review of progress by a high-level committee might be included to provide a regular and predictable opportunity to assess progress and take remedial action. Task-specific milestones can also be included to mark completion of major parts of the route.

As the identification of contingencies and milestones is both a strategic and technical exercise (depending on the type of roadblock), both the SC-ESR and TWG-ESR would be involved in the case of Guyana’s environmental statistics roadmap.

## Additional considerations

In the preceding, we have discussed the major elements of roadmaps in general and in the context of Guyana’s roadmap for environmental statistics. The discussion is not intended to be exhaustive but, rather, to provide DoE with basic guidance as it embarks on the creation of the roadmap. To that end, a few final comments are in order.

First, it is important to bear in mind that roadmaps must not be viewed as static. Doing so would be a recipe for failure, as it would eliminate the possibility of learning by doing. As a roadmap unfolds, people will learn what works and what does not, how to overcome obstacles and who to count on when challenges emerge. This knowledge can and should be used to improve the roadmap as the journey proceeds.

At the same time, frequently adjusting roadmaps is inefficient. It is preferable to adjust them only occasionally, after gathering substantial knowledge. This is one reason why embedding milestones in roadmaps is helpful. Milestones provide pre-determined points at which adjustments can be introduced, helping avoid the urge to make ad hoc adjustments every time something does not go according to plan. Ad hoc deviation from a roadmap is no better than starting off with no roadmap at all.

Second, and in the same vein, roadmaps should be understood as iterative and dynamic. Though they are high-level, it still takes time to come to agreement on roadmaps and they may never really be “finished”. For this reason, it is good to maintain the institutional structures used to create them (e.g., steering and technical working groups) even after they are complete. These groups may not meet frequently once the roadmap is in place, but maintaining them so they can meet when necessary is wise. Simply converting these structures into those needed to development and implement the associated action plan, while expedient, is not necessarily a good idea however. Action plans require different sets of skills than roadmaps (the latter being more strategic and the former being more operational), so the individuals charged with an action plan should not necessarily be the same as those who took care of getting the associated roadmap in place. Of course, some overlap in the membership of the two groups is to be expected, but they nonetheless need to be separate.

# Recommendations

In this section, we briefly summarize our recommendations to DoE on the steps it should take to establish Guyana’s roadmap for environmental statistics and ensure its full integration into the NSDS.

- DoE should actively pursue the engagement it has begun with the BoS in the NSDS process, expressing its clear commitment to ensuring full integration of environmental statistics in the strategy. Although DoE was not engaged in the process during its first two years, the process remains at an early enough stage that the opportunity for DoE to make a major contribution has in no way been lost. To capitalize on this opportunity, DoE should request that it be allowed to nominate a representative to the SC-NSDS (on the grounds that environmental conservation is at the heart of the GSDS). It should also offer its representative to the TWG-NSDS as chairperson for the working group.

- DoE should move quick to establish the institutional mechanisms required to develop and implement a roadmap for environmental statistics for Guyana. We suggest that these mechanisms be an SC-ESR and a TWG-ESR (as described in Section 3.2), as these would parallel the mechanisms proposed for managing the NSDS process. Other mechanisms are, of course, possible and DoE should explore approaches beyond what we have propose. In the end, whatever structures DoE decides upon must be both appropriate within the context of Guyana’s NESS and fully aligned with the structures put in place for the NSDS process.

- DoE should prepare clear and complete terms of reference and workplans for the groups ultimately established to develop the roadmap. Without effective terms of reference and workplans – established before the groups begin substantive work – these groups will almost certainly have difficulty fulfilling their mandates. The terms of reference and workplans must consider the need for alignment with the terms of reference and workplans established for the proposed SC-NSDS and TWG-NSDS (or whatever structures are ultimate put in place to develop the NSDS). Since DoE’s objective must be to ensure integration of environmental statistics into the NSDS, it is essential that the process to develop the environmental statistics roadmap unfold in a manner fully aligned with that for the NSDS.

- As a first order of business, the group charged with the leadership of the roadmap (e.g., our proposed SC-ESR) should confirm the starting point and vision we have articulated (see Section 4.1.1). We strongly recommend that the ESSAT (or some other established assessment tool) be used in establishing the starting point for the roadmap. We also strongly recommend that the needs of the GSDS, SDGs and other MEAs be carefully considered in establishing the country’s list of essential environmental statistics as part of the vision. Finally, we recommend that the UN FDES core set of environmental statistics be considered in defining this list as well.

- Once the starting point and vision are established, the other elements of the workplan (establishing current and future contexts, identifying constraints, identifying and prioritizing steps and identifying contingencies) can be developed. The order in which these are tackled will depend on the complexity and importance of each in the Guyanese context and we do not have enough information about this to provide clear recommendations. That said, it seems to us that the question of the possible evolution of the context for environmental statistics in Guyana is both complex and important given the country’s oil discoveries and the uncertainty about how this newfound wealth will affect its development. This aspect of the roadmap may, then, merit particular attention.

# Annex 1 – Agenda and presentation by Midsummer Analytics, Guyana environment statistics inception mission

### Agenda – Guyana inception mission

Strengthening the environmental dimension of the SDGs: Guyana´s Green State Development Strategy

Inception Workshop

7th February 2019

Georgetown, Guyana

Introduction

The project, “Strengthening the environmental dimensions of the sustainable development goals” (SDG-SED Guyana Project) is a component of a larger project implemented by UN Environment and its partners in four countries: Burkina Faso, Bangladesh, Colombia and Guyana. The Project’s goal is to strengthen the capacity of participating countries to:

- Collect sectoral data, derive national statistics, monitor and report on the country’s progress towards achievement of the environmental targets and indicators of the Sustainable Development Goals (SDGs) and Multilateral Environmental Agreements (MEAs), in accordance with national priorities;

- Establish institutional arrangements to integrate environmental considerations in the planning, implementation and reporting processes of the 2030 Sustainable Development Agenda and its related 17 goals and targets.

Background

The Government of Guyana is currently reviewing the draft Green State Development Strategy: Vision 2040, the development of which was supported by UN Environment in 2018 in partnership with the Department of Environment (DoE) of the Ministry of the Presidency (MoTP).  The draft Strategy describes the policy priorities for Guyana’s sustainable development over the next 20 years and addresses the three dimensions of sustainability: economic, social and environmental. The Strategy is integrated with the 2030 Agenda and its Sustainable Development Goals (SDGs) through support provided from the UN Country Team in Guyana along with other national and international partners, including the Secretariat of the Partnership for Action on the Green Economy (PAGE), of which Guyana is a member.

The challenge faced by the country however, is the availability of national targets and monitoring indicators for all eight development objectives (DOs) of the Green State Development Strategy: Vision 2040 for M&E during implementation.  Only one of the Strategy’s Development Objectives – DO3: Transition to Renewable Energy – has had stakeholder agreement on a firm national target: that is, the transition to “100% renewables” – and this is because of its inclusion in the country’s Nationally Determined Contribution under the Paris Agreement. Guyana is generally challenged by the lack of systematic, verifiable monitoring data and national statistics.

The SDG-SED Guyana project therefore provides an excellent opportunity to support the country’s planning for implementation and monitoring and evaluation (M&E) of the implementation of the Green State Development Strategy: Vision 2040. This foresees action through continued engagement of the GSDS networks of thematic expert groups, including public and private sector agencies and NGO partners.

Getting the relevant agencies and institutions to collectively plan, work together and coherently report on Guyana’s international environmental commitments is the main goal. As the national implementing partner, the Department of Environment (DoE) has expressed its desire for the SDG-SED Guyana Project to be integrated into efforts to support M&E reporting under Green State Development Strategy: Vision 2040. This will provide three-fold benefits: i) close existing M&E data gaps; ii) strengthen and build institutional capacity in the country for database management and M&E; and iii) improve overall capacity for environmental SDGs and MEAs implementation and reporting.

Objectives of the Workshop:

The objectives of the inception workshop are:

- To sensitise stakeholders on the SDG-SED Guyana project goals and objectives and its synergies with the Green State Development Strategy: Vision 2040;

- To understand national stakeholder needs and requirements for M&E data collection and monitoring;

- To identify and map key agency relationships, roles and responsibilities with a view to developing operational procedures for sustaining quality data collection and sharing;

- To achieve  consensus on SDG-SED Guyana project implementation arrangements.

Expected Workshop Outcomes:

- Participants have a clear understanding of their roles and responsibilities, as well as those of national institutions for M&E data collection, monitoring and reporting;

- Consensus achieved for a common workplan and project participation, cooperation and implementation mechanisms.

Workshop Agenda

| Time | Activity | Presenter |
| --- | --- | --- |
| 8:30 – 9:00 | Registration of Participants |  |
| 9:00 – 9:10 | Welcome and Introduction on Project | Ms. Ndibi Schwiers, Head, Department of Environment, Ministry of the Presidency |
| 9:10 - 9:15 | Remarks | Ms. Sonya Roopnauth; Director, Office of Budget, Ministry of Finance |
| 9:15 - 09:30 | Overview of the Green State Development Strategy: Vision 2040 | Ms. Deirdre Shurland; Senior Specialist, Project Manager, Green State Development Strategy |
| Session 1: SDG-SED Guyana Project Overview |  |  |
| 9:30 - 9:50 | Workshop Overview and Introduction to the SDG-SED Guyana Project | Ms. Piedad Martin; Regional Development Coordination Officer, UN Environment; Regional Office for Latin America and Caribbean (ROLAC) |
| 9:50 – 10:00 | Q & A |  |
| 10:00 – 10:20 | Statistical Component and Requirements of the SDG-SED Guyana Project | Mr. Francesco Gaetani – Regional Coordinator, Environment Under Review; UN Environment, ROLAC Mr. Robert Smith - International Consultant; Environmental Statistics |
| 10:20 - 10:30 | Interactive Q & A |  |
| 10:30 - 10:45 | Coffee Break |  |
| Session 2: Inter-active Group Work on Project Roles, Responsibilities and Cooperation Mechanisms |  |  |
| 10:45 – 12:15 | Interactive Group Session: - Key project results and outcomes - Roles and responsibilities - Cooperations mechanisms between and among agencies - M&E needs, protocols, requirements | Facilitation by [TBN] |
| 12:15 – 12:45 | Summary, conclusions and next Steps | Ms. Piedad Martin and Mr. Francesco Gaetani |
| 12:45 – 13:00 | Closing Remarks | Ms. Ndibi Schwiers, Director, Department of Environment, Ministry of the Presidency [TBC] |

Bilateral Meetings

The inception workshop will be complemented by bilateral meetings with the relevant stakeholders involved in data collection, monitoring and reporting of SDG and MEA- related targets; particularly those associated with the management of land, water, biodiversity and forests.  The bilateral engagements will include courtesy meetings with Heads of Agencies/Departments as well as technical sessions with senior technical staff. The general objective of these meetings is to discuss the national situation as it relates to data collection and sharing, and monitoring and reporting among the relevant stakeholders. The specific objectives are:

- To sensitise and  raise awareness on the SDG-SED Guyana Project  and initiate the process for inter-Agency sharing of technical knowledge;

- To discuss barriers to SDG-SED Guyana project outcomes;

- To discuss and agree on relevant GSDS Vision 2040 targets and indicators;

- To share and receive feedback on  the workplan and implementation arrangements;

Ms. Piedad Martin, Regional Development Coordination Officer, ROLAC will be engaging with environmental management agencies, including national focal points for UNCBD, UNCCD and UNFCCC, while   Mr. Francesco Gaetani and Mr. Robert Smith will focus on data collection and management protocols and the production of statistics.  The proposed schedule for the bilateral meetings is as tabulated below:

Table One:  Schedule for bilateral meetings

| Date | Time | Agency | Point Person | Designation | Contact Details | Meeting Leads |
| --- | --- | --- | --- | --- | --- | --- |
| 07-Feb | 14:00 - 14:45 hrs. | Ministry of Finance (MoF) | Ms. Sonya Roopnauth; Ms. Dominique Ambrose; Ms. Donna Levi | Director, Office of Budget;Economic & Financial Analyst; Head, Bilateral Department | 592-225-9408 sroopnauth@finance.gov.gy dambrose@finance.gov.gy | Ms. Piedad Martin |
|  |  | Bureau of Statistics (MoE) | Mr. Lennox Benjamin Ms. Vanessa Profitt Ms. Michelle Thorne | Chief Statistician Head, Demography Unit; Head, Information Systems Unit | 592-225-6150; 592-227-1155 montben@yahoo.com vprofitt@statisticsguyana.gov.gy | Mr. Francesco Gaetani/Mr. Robert Smith |
|  | 14:45 - 15:30 hrs. | Department of Environment, Ministry of the Presidency (MoTP) | Ms. Michelle Klass | Project Coordinator, Rio Project (EIMMS) | klass.michelle@yahoo.com | Ms. Piedad Martin |
|  |  | Ministry of Agriculture (MoA) | Ms. Delma Nedd | Permanent Secretary | 592-225-7526 ps.moagy@gmail.com | Mr. Francesco Gaetani/ Mr. Robert Smith |
|  |  |  | Ms. Natasha Beerjit | Coordinator, M&E Unit | 592-2262219; nbeerjit@gmail.com |  |
|  | 15:30 - 16:15 hrs. | Ministry of Natural Resources (MNR) | Mr. Joslyn McKenzie | Permanent Secretary | 592-231-2506 | Ms. Piedad Martin |
|  |  |  | Mr. Veetal Rajkumar Dr. Rudy Jadoopat | Head; Policy and Planning Coordination National Coordinator; GYEITI | vrajkumar@nre.gov.gy 592-231- 2538 rudyjadoopat@gyeiti.org |  |
|  |  | Project Implementation Unit, GRIF Secretariat (MoTP) | Dr. Marlon Bristol | Head, Project Management Department | marlon.a.bristol@gmail.com | Mr. Francesco Gaetani/ Mr. Robert Smith |
|  | 16:15 - 17:00 hrs. | Guyana Forestry Commission (MNR) | Mr. James Singh | Commissioner |  | Ms. Piedad Martin |
|  |  |  | Ms. Pradeepa Bholanath/Ms. Nasheta Dewnaught | Project Coordinator Coordinator, National REDD* Secretariat | 592-226-7271 - project.coordinator@forestry.gov.gy |  |
| 08-Feb | 09:00 - 9:45 hrs | Environmental Protection Agency (MoTP) | Dr. Vincent Adams Ms. Stacy Lord | Executive Director SEO; Resource Mgt. Programme | 592-225-5467; 592-225-5471 592 – 225-5467(Ext. 230); slord@epaguyana.org | Ms. Piedad Martin |
|  |  | National Data Management Authority ( Ministry of Public Telecommunications) | Mr. Floyd Levi | Chairman | 592-231-8825; Floyd.levi@egov.gy | Mr. Francesco Gaetani and Mr. Robert Smith |
|  | 09:45 -10:30 hrs | Guyana Lands & Surveys Commission (MoTP) | Ms. Andrea Mahammad | Head; Land Use Division | 592-226-6490 | Ms. Piedad Martin |
|  |  |  | Mr. Chetwynd Osborne | Liaison Officer; UNCCD | 592-226-6490 |  |
|  | 10:30 - 11:15 hrs. | HydroMet Services (MoA) | Dr. Garvin Cummings | Deputy Chief HydroMet Officer | 592-225-4247; hydromet.guyana@yahoo.com | Mr. Francesco Gaetani and Mr. Robert Smith |
|  | 11:15 - 12:00 hrs | WWF-Guianas | Ms. Aiesha Williams | Country Coordinator | 592-223-7802; awilliams@wwf.org | Ms. Piedad Martin |
|  |  | National Agricultural Research and Extension Institute (NAREI) | Dr. Oudho Homenauth | CEO | 592-220-2249; oudhomenauth@gmail.com | Mr. Francesco Gaetani and Mr. Robert Smith |

### Presentation by Midsummer Analytics – Guyana inception workshop

# Annex 2 – Agenda and presentations by Midsummer Analytics – Guyana environment statistics training workshop

## Agenda – Guyana environment statistics workshop

Workshop

“Strengthening the Environmental Dimension of the SDGs:

Guyana’s Green State Development Strategy: Vision 2040”

Enhancing Environmental Statistics for Measurement and Evaluation: Implementing Guyana’s Green State Development Strategy: Vision 2040

Date: 6th - 8th August 2019			Venue:  Roraima Duke Lodge, 94-95 Duke St. Kingston. Georgetown

Workshop Agenda

| Time | Discussion Item | Speakers |
| --- | --- | --- |
| Day 1: August 6th 2019 |  |  |
| 8:30 am – 9:00 am | Registration of Participants |  |
| Session 1: Welcome and Overview of Objectives |  |  |
| 9:00 am – 9:10 am | Welcome and Opening Remarks | Ms. Ndibi Schwiers, Director, Department of Environment, Ministry of the Presidency, and Country Partner |
| 9:10 am - 9:25 am | National Statistics: Its relevance to evidence-based decision-making and international reporting | Bureau of Statistics, Ministry of Finance |
| 9:25 am – 09:40 am | Building Guyana’s science-policy interface: A Regional Perspective | Mr. Francesco Gaetani, Coordinator Environment Under Review, United Nations Environment Programme (ROLAC – Panama) |
| 9:40am – 10:00am | Role of the UN system in supporting Guyana’s achievement of the 2030 Agenda for Sustainable Development | Ms. Mikiko Tanaka - UN Resident Coordinator; Guyana |
| 10:00am – 10:15 am | Coffee Break |  |
| 10:15am – 10:20am | Instant Poll |  |
| Session 2: Fundamental Principles of Official National Statistics |  |  |
| 10:20am – 12:30pm | Workshop Overview (Objectives and approach) Creating a Statistical Roadmap for Guyana – What is needed and how to get there | Mr. Robert Smith Principal, Midsummer Analytics |
|  | Presentation and Q&A UN Fundamental Principles of Official National Statistics |  |
| 12:30pm – 1:30pm | Lunch |  |
| 1:30pm - 2:30pm | Small group discussions Guyana and the UN Fundamental Principles | Mr. Robert Smith assisted by Group moderators and rapporteurs |
| Session 3: UN Framework for the Development of Environment Statistics |  |  |
| 2:30pm – 3:30pm | Presentation and Q&A | Mr. Robert Smith |
|  | UN Framework for the Development of Environment Statistics (FDES) |  |
| 3:30pm – 3:45pm | Coffee Break |  |
| 3:45pm – 4:30pm | UN Environment Statistics Self-assessment Tool (ESSAT) | Mr. Robert Smith |
| 4:30pm – 4:45pm | Wrap-up & Summary of the day and brief introduction to Day 2 |  |

| Time | Activity | Speakers |
| --- | --- | --- |
| Day 2: August 7th 2019 |  |  |
| 9:00am – 9:15am | Review of Day 1 Overview of Day 2 and follow up on any outstanding points from Day 1 | Mr. Robert Smith |
| Session 4: Building Guyana’s Roadmap for Environmental Statistics |  |  |
| 9:15am – 9:45am | Presentation and Q&A Working Group on Environmental Indicators in the Framework of Latin America and Caribbean Initiative for Sustainable Development (ILAC) | Mr. Francesco Gaetani - Regional Coordinator, Environment Under Review, Regional Office for Latin America and the Caribbean (ROLAC), UN Environment |
| 9:45am – 10:30am | Small group discussions | Mr. Robert Smith - Assisted by Group moderators and rapporteurs |
|  | Roadmap Part I: Assessing the current situation in Guyana |  |
| 10:30am – 10:45am | Coffee Break |  |
| 10:45am – 11:45am | Small group discussions (cont’d): | Groups presentations (10 mins) |
|  | Roadmap Part I - Assessing the current situation in Guyana | Mr. Robert Smith |
| 11:45am – 12:30pm | Presentation and Q&A: |  |
|  | Identifying needs, gaps and priorities for Guyana's environmental statistics for multilateral environmental agreements (MEAs) and Sustainable Development Goals (SDGs) |  |
| 12:30pm – 1:30pm | Lunch |  |
| 1:30pm – 2:30pm | Presentation and Q&A (cont'd) | Mr. Robert Smith |
|  | Identifying needs, gaps and priorities for Guyana's environmental statistics for multilateral environmental agreements (MEAs) and Sustainable Development Goals (SDGs) |  |
| Session 5: [Sectoral] Statistics |  |  |
| 2:30pm - 3:00pm | Statistical Presentation | Ms. Shevon Wood - Head, Energy and Energy Statistics Division, Guyana Energy Agency |
|  | Brief overview of Guyana’s energy statistics The objective is to identify the main elements of Guyana’s energy statistics. These elements will be the focus of the small group discussions in the next session |  |
| 3:00pm – 3:30pm | Presentation and Q&A Energy statistics – International frameworks and their relevance to Guyana Energy statistics | Robert Smith |
| 3:30pm – 3:45pm | Coffee Break |  |
| 3:45pm – 4:30pm | Small group discussions Roadmap Part II - Identifying needs/gaps/ priorities for energy statistics | Mr. Francesco Gaetani assisted by Group moderators and rapporteurs |
| 4:30pm – 4:45pm | Wrap-up Summary of the day and brief intro to Day 3 | Mr. Francesco Gaetani; Mr. Robert Smith |

| Time | Activity | Speakers |
| --- | --- | --- |
| Day 3: August 8th (Session 5 cont’d) |  |  |
| 9:00am – 9:15am | Presentation and Q&A: Overview of day 3 and follow up on any outstanding points from day 2 | Mr. Robert Smith |
| 9:15am – 9:45am | Presentations: Brief overview of Guyana’s land use/cover statistics | Ms. Andrea Mahammed, Head – Land Policy, Planning and Project Division, Guyana Lands and Surveys Commission |
| 9:45am - 10:30am | Presentation and Q&A: Land-use statistics – International frameworks and their relevance to Guyana | Mr. Robert Smith |
| 10:30am – 10:45am | Coffee Break |  |
| 10:45 am – 12:30pm | Small group discussions: Roadmap Part II - Identifying needs/gaps/priorities for land statistics | Mr. Francesco Gaetani - Assisted by Group moderators and rapporteurs |
| 12:30pm – 1:30pm | Lunch |  |
| Session 5: Tying it all together |  |  |
| 1:30pm – 2:30pm | Presentation and Q&A: | Mr. Robert Smith |
|  | Measuring Guyana's forest sector in the context of the SDGs and the Green State Development Strategy Vision 2040: |  |
|  | Tying it all together |  |
| Session 6: Workshop Wrap-up and closure |  |  |
| 2:30pm – 3:00pm | Wrap-up: | Mr. Francesco Gaetani; Mr. Robert Smith |
|  | Discussion of workshop outcomes; presentation of participation certificates |  |
| Instant Poll |  |  |

## Presentations by Midsummer Analytics – Guyana environmental statistics training workshop

Note that we were, in fact, contracted to carry out an assessment of Guyana’s capacity to produce environmental statistics in support of its reporting on the UN sustainable development goals. However, the UNEP regional office in Panama requested that we focus instead on assisting the Department of Environment in development of a roadmap for environmental statistics. For this reason, the work outlined in this report does not correspond fully to our original terms of reference. No formal amendment to the contract was made and the change in terms of reference was accepted on the basis of an informal agreement. Note that the roadmap relies on an informal assessment of capacity as a basis for selecting areas for future development.

Ms. Ndibi Schwiers, Head, Department of Environment, Ministry of the Presidency.

Ms. Piedad Martin Regional Development Coordination Officer, UN Environment; Regional Office for Latin America and Caribbean.

As noted above, this focus on roadmap development was decided upon informally during the course of the project and does not align with our original terms of reference as laid out in our contract.

This section draws upon a presentation made by Mr. David Clement, NSDS Consultant, during a validation workshop for the design of the NSDS held in at the offices of the Guyana Bureau of Statistics, Georgetown on October 17, 2019. A copy of this presentation was provided to us by Mr. Eustace Alexander, National Technical Expert, GSDS Coordination Office.

See https://finance.gov.gy/media/bureau-of-statistics-launches-national-strategy-for-the-development-of-statistics-data-for-better-developmental-planning-to-be-strengthened/

PARIS21 is an international organization mandated to assist developing countries improve their national statistics. More information about PARIS21 and its efforts to assist countries in the preparation of national statistical development strategies can be found here: https://paris21.org/national-strategy-development-statistics-nsds.

A national statistical system is the combination of statistical organisations and units within a country that jointly collect, process and disseminate statistics on behalf of the national government. Members of the system typically include the national statistics office, playing a coordinating role, and units within line departments and agencies responsible for producing “sectoral” statistics (e.g., agricultural or health statistics). The statistics produced by these bodies are referred to collectively as “official statistics”. According to the United Nations’ Fundamental Principles of Official Statistics, official statistics provide an indispensable element in the information system of democratic societies, serving governments, businesses and the public with data about the economic, demographic, social and environmental situation of nation states (see https://unstats.un.org/unsd/dnss/gp/FP-New-E.pdf).

We were unable to obtain a copy of this assessment.

The results of this analysis are summarized in an annex to the report referred to in Footnote 12 below.

See National Strategy for the Development of Statistics – Roadmap (https://paris21.org/sites/default/files/2018-07/Guyana-NSDS-Roadmap-web.pdf).

See the CARICOM Statistics Model Bill (https://caricom.org/document-Library/view-document/the-statistics-model-bill).

See https://doe.gov.gy/gsds/.

If DoE’s current financial and human resources do not permit it to effectively play this role, it is encouraged to highlight this to the Ministry of Finance and to discuss possibilities for short-term funding to augments its budget. In particular, if any external funding is being made available to Guyana for the development of the NSDS from PARIS21 or other multi-lateral development organizations, DoE is encouraged to apply for a share of this funding to support its role in the process.

Relevant departments/agencies include all those entities of the government of Guyana that are significant producers or users of environmental statistics.

Note that the chairperson of the SC-ESR should also be a member of the high-level guiding committee of the NSDS to ensure effective coordination and communications between the two groups.

Note that the chairperson of the TWG-ESR should also be a member of the SC-ESR to ensure effective coordination and communications between the two groups.

We understand that a National Information Monitoring and Management System is being proposed as part of the NSDS.

See, in particular, the second presentation in Annex 2, titled “Creating a statistical roadmap for Guyana – What is needed and how to get there” and the ninth presentation, titled “Towards a Roadmap for Guyana’s Environmental Statistics”.

See Environmental Data Gap Analysis for the Project: Reporting System for MEA Implementation – Environmental Information Management Consultancy (available from Francesco Gaetani, UNEP Panama Office).

The TWG-ESR could be assigned the task of reviewing Guyana’s existing environmental statistics using the ESSAT and/or regional assessment tools, but the actual confirmation of the starting point should fall to the SC-ESR.

See the presentation titled “UN Framework for the Development of Environment Statistics” in Annex 2; the sixth presentation included in the annex.

This material is drawn from the aforementioned presentation by David Clement (see Footnote 6).

Our knowledge of existing production systems for environmental statistics in Guyana is too limited for us to be more specific in identifying the steps required in the roadmap for environmental statistics.